## DR APP VM Details
Component | Region | Azure VM Name | VM Primary IP | Virtual Hostname1 | VM Secondary IP1 | SID | Environment Type | OS Version | OS Type | Series | ASR Region | ASR Resource Group | ASR VNET Resource Group | ASR VNET | ASR Subnet | ASR Availablity Set | ASR PPG Name | Azure VM Name | VM Primary IP | Virtual Hostname1 | VM Secondary IP1 | ASR Primary IP | ASR Secondary IP | Load Balancer Name | Load Balancer Front end IP | LB
SAP BusinessObjects Data Services on HANA (App ) | Primary Region | bdpcs01use2pr | 10.213.34.5 | sapbdpcs01pr | 10.213.34.6 | BDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bdpap-cus-pr | sap-ppg-bdp-cus-pr | bdpcs01use2pr | 10.213.34.5 | sapbdpcs01pr | 10.213.34.6 | 10.214.24.239 | 10.214.24.240 | sap-ilb-bdpap-cus-pr-01 | 10.214.24.105 | NA
SAP BusinessObjects Data Services on HANA (App ) | Primary Region | bdpap02use2pr | 10.213.34.7 | sapbdpap02pr | 10.213.34.8 | BDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bdpap-cus-pr | sap-ppg-bdp-cus-pr | bdpap02use2pr | 10.213.34.7 | sapbdpap02pr | 10.213.34.8 | 10.214.24.237 | 10.214.24.238 |  |  | NA
SAP BusinessObjects Data Services on HANA (App ) | Primary Region | bdpap03use2pr | 10.213.34.9 | sapbdpap03pr | 10.213.34.10 | BDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bdpap-cus-pr | sap-ppg-bdp-cus-pr | bdpap03use2pr | 10.213.34.9 | sapbdpap03pr | 10.213.34.10 | 10.214.24.245 | 10.214.24.246 | NA | NA | NA
SAP BusinessObjects Data Services on HANA (App ) | Primary Region | bdpap04use2pr | 10.213.34.11 | sapbdpap04pr | 10.213.34.12 | BDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bdpap-cus-pr | sap-ppg-bdp-cus-pr | bdpap04use2pr | 10.213.34.11 | sapbdpap04pr | 10.213.34.12 | 10.214.24.247 | 10.214.24.248 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Primary Region | bipcs01use2pr | 10.213.34.13 | sapbipcs01pr | 10.213.34.14 | BIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bipap-cus-pr | sap-ppg-bip-cus-pr | bipcs01use2pr | 10.213.34.13 | sapbipcs01pr | 10.213.34.14 | 10.214.24.173 | 10.214.24.174 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Primary Region | bipap02use2pr | 10.213.34.15 | sapbipap02pr | 10.213.34.16 | BIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bipap-cus-pr | sap-ppg-bip-cus-pr | bipap02use2pr | 10.213.34.15 | sapbipap02pr | 10.213.34.16 | 10.214.24.191 | 10.214.24.192 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Primary Region | bipap03use2pr | 10.213.34.17 | sapbipap03pr | 10.213.34.18 | BIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bipap-cus-pr | sap-ppg-bip-cus-pr | bipap03use2pr | 10.213.34.17 | sapbipap03pr | 10.213.34.18 | 10.214.24.187 | 10.214.24.188 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Primary Region | bipap04use2pr | 10.213.34.19 | sapbipap04pr | 10.213.34.20 | BIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bipap-cus-pr | sap-ppg-bip-cus-pr | bipap04use2pr | 10.213.34.19 | sapbipap04pr | 10.213.34.20 | 10.214.24.189 | 10.214.24.190 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Primary Region | bipap05use2pr | 10.213.34.21 | sapbipap05pr | 10.213.34.22 | BIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bipap-cus-pr | sap-ppg-bip-cus-pr | bipap05use2pr | 10.213.34.21 | sapbipap05pr | 10.213.34.22 | 10.214.24.185 | 10.214.24.186 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Primary Region | bipap06use2pr | 10.213.34.23 | sapbipap06pr | 10.213.34.24 | BIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bipap-cus-pr | sap-ppg-bip-cus-pr | bipap06use2pr | 10.213.34.23 | sapbipap06pr | 10.213.34.24 | 10.214.24.183 | 10.214.24.184 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Primary Region | bipap07use2pr | 10.213.34.25 | sapbipap07pr | 10.213.34.26 | BIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bipap-cus-pr | sap-ppg-bip-cus-pr | bipap07use2pr | 10.213.34.25 | sapbipap07pr | 10.213.34.26 | 10.214.24.179 | 10.214.24.180 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Primary Region | bipap08use2pr | 10.213.34.27 | sapbipap08pr | 10.213.34.28 | BIP | Production | Win_2016 | Win_2016 | D4as_v4 | Central US | sap-rg-bip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-bipap-cus-pr | sap-ppg-bip-cus-pr | bipap08use2pr | 10.213.34.27 | sapbipap08pr | 10.213.34.28 | 10.214.24.175 | 10.214.24.176 | NA | NA | NA
Fiori for S/4HANA On-Premise Edition (ASCS ) | Primary Region | fipcs01use2pr | 10.213.34.31 | sapfipcs01pr | 10.213.34.32 | FIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-fipap-cus-pr | sap-ppg-fip-cus-pr | fipcs01use2pr | 10.213.34.31 | sapfipcs01pr | 10.213.34.32 | 10.214.24.197 | 10.214.24.198 | sap-ilb-fipapp-cus-pr-01 | 10.214.24.108 | ASCS
Fiori for S/4HANA On-Premise Edition (ERS ) | Primary Region | fipcs02use2pr | 10.213.34.33 | sapfipcs02pr | 10.213.34.34 | FIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-fipap-cus-pr | sap-ppg-fip-cus-pr | fipcs02use2pr | 10.213.34.33 | sapfipcs02pr | 10.213.34.34 | 10.214.24.195 | 10.214.24.196 |  | 10.214.24.109 | ERS
Fiori for S/4HANA On-Premise Edition (App ) | Primary Region | fipap03use2pr | 10.213.34.35 | sapfipap03pr | 10.213.34.36 | FIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-fipap-cus-pr | sap-ppg-fip-cus-pr | fipap03use2pr | 10.213.34.35 | sapfipap03pr | 10.213.34.36 | 10.214.24.221 | 10.214.24.222 | NA | NA | NA
Fiori for S/4HANA On-Premise Edition (App ) | Primary Region | fipap04use2pr | 10.213.34.37 | sapfipap04pr | 10.213.34.38 | FIP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-fipap-cus-pr | sap-ppg-fip-cus-pr | fipap04use2pr | 10.213.34.37 | sapfipap04pr | 10.213.34.38 | 10.214.24.199 | 10.214.24.200 | NA | NA | NA
S/4HANA On-Premise Edition (ASCS ) | Primary Region | hapcs01use2pr | 10.213.34.39 | saphapcs01pr | 10.213.34.40 | HAP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-hapap-cus-pr | sap-ppg-hap-cus-pr | hapcs01use2pr | 10.213.34.39 | saphapcs01pr | 10.213.34.40 | 10.214.24.201 | 10.214.24.202 | sap-ilb-hapapp-cus-pr-01 | 10.214.24.106 | ASCS
S/4HANA On-Premise Edition (ERS ) | Primary Region | hapcs02use2pr | 10.213.34.41 | saphapcs02pr | 10.213.34.42 | HAP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-hapap-cus-pr | sap-ppg-hap-cus-pr | hapcs02use2pr | 10.213.34.41 | saphapcs02pr | 10.213.34.42 | 10.214.24.213 | 10.214.24.214 |  | 10.214.24.107 | ERS
S/4HANA On-Premise Edition (App ) | Primary Region | hapap03use2pr | 10.213.34.43 | saphapap03pr | 10.213.34.44 | HAP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-hapap-cus-pr | sap-ppg-hap-cus-pr | hapap03use2pr | 10.213.34.43 | saphapap03pr | 10.213.34.44 | 10.214.24.217 | 10.214.24.218 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | Primary Region | hapap04use2pr | 10.213.34.45 | saphapap04pr | 10.213.34.46 | HAP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-hapap-cus-pr | sap-ppg-hap-cus-pr | hapap04use2pr | 10.213.34.45 | saphapap04pr | 10.213.34.46 | 10.214.24.210 | 10.214.24.211 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | Primary Region | hapap05use2pr | 10.213.34.47 | saphapap05pr | 10.213.34.48 | HAP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-hapap-cus-pr | sap-ppg-hap-cus-pr | hapap05use2pr | 10.213.34.47 | saphapap05pr | 10.213.34.48 | 10.214.24.206 | 10.214.24.207 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | Primary Region | hapap06use2pr | 10.213.34.49 | saphapap06pr | 10.213.34.50 | HAP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-hapap-cus-pr | sap-ppg-hap-cus-pr | hapap06use2pr | 10.213.34.49 | saphapap06pr | 10.213.34.50 | 10.214.24.205 | 10.214.24.212 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | Primary Region | hapap07use2pr | 10.213.34.51 | saphapap07pr | 10.213.34.52 | HAP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-hapap-cus-pr | sap-ppg-hap-cus-pr | hapap07use2pr | 10.213.34.51 | saphapap07pr | 10.213.34.52 | 10.214.24.208 | 10.214.24.209 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | Primary Region | hapap08use2pr | 10.213.34.53 | saphapap08pr | 10.213.34.54 | HAP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-hapap-cus-pr | sap-ppg-hap-cus-pr | hapap08use2pr | 10.213.34.53 | saphapap08pr | 10.213.34.54 | 10.214.24.215 | 10.214.24.216 | NA | NA | NA
S/4HANA On-Premise Edition - MDG + GRC (ASCS ) | Primary Region | mdpcs01use2pr | 10.213.34.55 | sapmdpcs01pr | 10.213.34.56 | MDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-mdpap-cus-pr | sap-ppg-mdp-cus-pr | mdpcs01use2pr | 10.213.34.55 | sapmdpcs01pr | 10.213.34.56 | 10.214.24.223 | 10.214.24.224 | sap-ilb-mdpapp-cus-pr-01 | 10.214.24.111 | ASCS
S/4HANA On-Premise Edition - MDG + GRC (ERS ) | Primary Region | mdpcs02use2pr | 10.213.34.57 | sapmdpcs02pr | 10.213.34.58 | MDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-mdpap-cus-pr | sap-ppg-mdp-cus-pr | mdpcs02use2pr | 10.213.34.57 | sapmdpcs02pr | 10.213.34.58 | 10.214.24.229 | 10.214.24.230 | sap-ilb-mdpapp-cus-pr-01 | 10.214.24.110 | ERS
S/4HANA On-Premise Edition - MDG + GRC (App ) | Primary Region | mdpap03use2pr | 10.213.34.59 | sapmdpap03pr | 10.213.34.60 | MDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-mdpap-cus-pr | sap-ppg-mdp-cus-pr | mdpap03use2pr | 10.213.34.59 | sapmdpap03pr | 10.213.34.60 | 10.214.24.225 | 10.214.24.226 | NA | NA | NA
S/4HANA On-Premise Edition - MDG + GRC (App ) | Primary Region | mdpap04use2pr | 10.213.34.61 | sapmdpap04pr | 10.213.34.62 | MDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-mdpap-cus-pr | sap-ppg-mdp-cus-pr | mdpap04use2pr | 10.213.34.61 | sapmdpap04pr | 10.213.34.62 | 10.214.24.231 | 10.214.24.232 | NA | NA | NA
S/4HANA On-Premise Edition - MDG + GRC (App ) | Primary Region | mdpap05use2pr | 10.213.34.63 | sapmdpap05pr | 10.213.34.64 | MDP | Production | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-mdpap-cus-pr | sap-ppg-mdp-cus-pr | mdpap05use2pr | 10.213.34.63 | sapmdpap05pr | 10.213.34.64 | 10.214.24.227 | 10.214.24.228 | NA | NA | NA
Apache Webserver (Non-SAP ) | Primary Region | mfpap01use2pr | 10.213.33.6 | sapmfpap01pr | 10.213.33.7 | MFP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-mfp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-mgmt-qa | sap-avs-mfpap-cus-pr | sap-ppg-mfp-cus-pr | mfpap01use2pr | 10.213.33.6 | sapmfpap01pr | 10.213.33.7 | 10.214.24.219 | 10.214.24.220 | NA | NA | NA
SAP Business Process Automation by Redwood (ASCS ) | Primary Region | rbpcs01use2pr | 10.213.34.69 | saprbpcs01pr | 10.213.34.70 | RBP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-rbp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-rbpap-cus-pr | sap-ppg-rbp-cus-pr | rbpcs01use2pr | 10.213.34.69 | saprbpcs01pr | 10.213.34.70 | 10.214.24.193 | 10.214.24.194 | sap-ilb-rbpapp-cus-pr-01 | 10.214.24.113 | ASCS
SAP Business Process Automation by Redwood (ERS ) | Primary Region | rbpcs02use2pr | 10.213.34.71 | saprbpcs02pr | 10.213.34.72 | RBP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-rbp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-rbpap-cus-pr | sap-ppg-rbp-cus-pr | rbpcs02use2pr | 10.213.34.71 | saprbpcs02pr | 10.213.34.72 | 10.214.24.203 | 10.214.24.204 |  | 10.214.24.112 | ERS
SAP Solution Manager 7.2 (JAVA) (ASCS+PAS ) | Primary Region | sjpcs01use2pr | 10.213.34.73 | sapsjpcs01pr | 10.213.34.74 | SJP | Production | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-sjp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-sjpap-cus-pr | sap-ppg-sjp-cus-pr | sjpcs01use2pr | 10.213.34.73 | sapsjpcs01pr | 10.213.34.74 | 10.214.24.181 | 10.214.24.182 | sap-ilb-sjpapp-cus-pr-01 | 10.214.24.115 | ASCS
SAP Solution Manager 7.2 (JAVA) (ERS ) | Primary Region | sjpcs02use2pr | 10.213.34.75 | sapsjpcs02pr | 10.213.34.76 | SJP | Production | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-sjp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-sjpap-cus-pr | sap-ppg-sjp-cus-pr | sjpcs02use2pr | 10.213.34.75 | sapsjpcs02pr | 10.213.34.76 | 10.214.24.177 | 10.214.24.178 |  | 10.214.24.114 | ERS
SAP Solution Manager 7.2 (ABAP) (ASCS+PAS ) | Primary Region | smpcs01use2pr | 10.213.34.77 | sapsmpcs01pr | 10.213.34.78 | SMP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-smp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-smpap-cus-pr | sap-ppg-smp-cus-pr | smpcs01use2pr | 10.213.34.77 | sapsmpcs01pr | 10.213.34.78 | 10.214.24.249 | 10.214.24.250 | sap-ilb-smpapp-cus-pr-01 | 10.214.24.117 | ASCS
SAP Solution Manager 7.2 (ABAP) (ERS ) | Primary Region | smpcs02use2pr | 10.213.34.79 | sapsmpcs02pr | 10.213.34.80 | SMP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-smp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-smpap-cus-pr | sap-ppg-smp-cus-pr | smpcs02use2pr | 10.213.34.79 | sapsmpcs02pr | 10.213.34.80 | 10.214.24.251 | 10.214.24.252 |  | 10.214.24.116 | ERS
IaaS Basic (Vertex SIC) | Primary Region | vspap01use2pr | 10.213.33.8 | sapvspap01pr | 10.213.33.9 | VSP | Production | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-vsp-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-mgmt-qa | sap-avs-vspap-cus-pr | sap-ppg-vsp-cus-pr | vspap01use2pr | 10.213.33.8 | sapvspap01pr | 10.213.33.9 | 10.214.24.243 | 10.214.24.244 | NA | NA | NA
SAP Webdispatcher (App ) | Primary Region | wpdap01use2pr | 10.213.34.81 | sapwd1ap01pr | 10.213.34.82 | WD1 | Production | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-wpd-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-wpdap-cus-pr | sap-ppg-wpd-cus-pr | wpdap01use2pr | 10.213.34.81 | sapwd1ap01pr | 10.213.34.82 | 10.214.24.235 | 10.214.24.236 | NA | NA | NA
SAP Webdispatcher (App ) | Primary Region | wpdap02use2pr | 10.213.34.83 | sapwd2ap02pr | 10.213.34.84 | WD2 | Production | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-wpd-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-wpdap-cus-pr | sap-ppg-wpd-cus-pr | wpdap02use2pr | 10.213.34.83 | sapwd2ap02pr | 10.213.34.84 | 10.214.24.233 | 10.214.24.234 | NA | NA | NA
Wily Introscope | Primary Region | wlyap01use2pr | 10.213.34.85 | sapwlyap01pr | 10.213.34.86 | Wily | Production | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-wly-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-app-qa | sap-avs-wlyap-cus-pr | sap-ppg-wly-cus-pr | wlyap01use2pr | 10.213.34.85 | sapwlyap01pr | 10.213.34.86 | 10.214.24.253 | 10.214.24.254 | NA | NA | NA
Unmanaged IaaS WTS service for customer (Non-SAP ) | Primary Region | iaaswp1use2pr | 10.213.33.12 | sapwp1ap01pr | 10.213.33.13 | WP1 | Production | WindowsServer | Win_2016 | D8as_v4 | Central US | sap-rg-wts-cus-pr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-mgmt-qa | sap-avs-wtsap-cus-pr | sap-ppg-wts-cus-pr | iaaswp1use2pr | 10.213.33.12 | sapwp1ap01pr | 10.213.33.13 | 10.214.24.241 | 10.214.24.242 | NA | NA | NA
SAP Router | Primary Region | saproutuse2pr | 10.213.1.100 |  |  | saprouter | Production | SLES-SAP 12 SP4 | Suse_Linux |  | Central US | [6 empty] | saproutuse2pr | 10.213.1.100

## Sheet3
Component | OS Version | OS Type | Series | ASR Region | ASR Resource Group | Azure VM Name | ASR Primary IP | Virtual Hostname1 | ASR Secondary IP | Load Balancer Name | Load Balancer Front end IP | LB
SAP BusinessObjects Data Services on HANA (App ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bdp-cus-pr | bdpcs01use2pr | 10.214.24.239 | sapbdpcs01pr | 10.214.24.240 | sap-ilb-bdpap-cus-pr-01 | 10.214.24.105 | NA
SAP BusinessObjects Data Services on HANA (App ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bdp-cus-pr | bdpap02use2pr | 10.214.24.237 | sapbdpap02pr | 10.214.24.238 |  |  | NA
SAP BusinessObjects Data Services on HANA (App ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bdp-cus-pr | bdpap03use2pr | 10.214.24.245 | sapbdpap03pr | 10.214.24.246 | NA | NA | NA
SAP BusinessObjects Data Services on HANA (App ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bdp-cus-pr | bdpap04use2pr | 10.214.24.247 | sapbdpap04pr | 10.214.24.248 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | bipcs01use2pr | 10.214.24.173 | sapbipcs01pr | 10.214.24.174 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | bipap02use2pr | 10.214.24.191 | sapbipap02pr | 10.214.24.192 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | bipap03use2pr | 10.214.24.187 | sapbipap03pr | 10.214.24.188 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | bipap04use2pr | 10.214.24.189 | sapbipap04pr | 10.214.24.190 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | bipap05use2pr | 10.214.24.185 | sapbipap05pr | 10.214.24.186 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | bipap06use2pr | 10.214.24.183 | sapbipap06pr | 10.214.24.184 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-bip-cus-pr | bipap07use2pr | 10.214.24.179 | sapbipap07pr | 10.214.24.180 | NA | NA | NA
SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | Win_2016 | Win_2016 | D4as_v4 | Central US | sap-rg-bip-cus-pr | bipap08use2pr | 10.214.24.175 | sapbipap08pr | 10.214.24.176 | NA | NA | NA
Fiori for S/4HANA On-Premise Edition (ASCS ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-pr | fipcs01use2pr | 10.214.24.197 | sapfipcs01pr | 10.214.24.198 | sap-ilb-fipapp-cus-pr-01 | 10.214.24.108 | ASCS
Fiori for S/4HANA On-Premise Edition (ERS ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-pr | fipcs02use2pr | 10.214.24.195 | sapfipcs02pr | 10.214.24.196 |  | 10.214.24.109 | ERS
Fiori for S/4HANA On-Premise Edition (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-pr | fipap03use2pr | 10.214.24.221 | sapfipap03pr | 10.214.24.222 | NA | NA | NA
Fiori for S/4HANA On-Premise Edition (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-pr | fipap04use2pr | 10.214.24.199 | sapfipap04pr | 10.214.24.200 | NA | NA | NA
S/4HANA On-Premise Edition (ASCS ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | hapcs01use2pr | 10.214.24.201 | saphapcs01pr | 10.214.24.202 | sap-ilb-hapapp-cus-pr-01 | 10.214.24.106 | ASCS
S/4HANA On-Premise Edition (ERS ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | hapcs02use2pr | 10.214.24.213 | saphapcs02pr | 10.214.24.214 |  | 10.214.24.107 | ERS
S/4HANA On-Premise Edition (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | hapap03use2pr | 10.214.24.217 | saphapap03pr | 10.214.24.218 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | hapap04use2pr | 10.214.24.210 | saphapap04pr | 10.214.24.211 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | hapap05use2pr | 10.214.24.206 | saphapap05pr | 10.214.24.207 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | hapap06use2pr | 10.214.24.205 | saphapap06pr | 10.214.24.212 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | hapap07use2pr | 10.214.24.208 | saphapap07pr | 10.214.24.209 | NA | NA | NA
S/4HANA On-Premise Edition (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-hap-cus-pr | hapap08use2pr | 10.214.24.215 | saphapap08pr | 10.214.24.216 | NA | NA | NA
S/4HANA On-Premise Edition - MDG + GRC (ASCS ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | mdpcs01use2pr | 10.214.24.223 | sapmdpcs01pr | 10.214.24.224 | sap-ilb-mdpapp-cus-pr-01 | 10.214.24.111 | ASCS
S/4HANA On-Premise Edition - MDG + GRC (ERS ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | mdpcs02use2pr | 10.214.24.229 | sapmdpcs02pr | 10.214.24.230 |  | 10.214.24.110 | ERS
S/4HANA On-Premise Edition - MDG + GRC (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | mdpap03use2pr | 10.214.24.225 | sapmdpap03pr | 10.214.24.226 | NA | NA | NA
S/4HANA On-Premise Edition - MDG + GRC (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | mdpap04use2pr | 10.214.24.231 | sapmdpap04pr | 10.214.24.232 | NA | NA | NA
S/4HANA On-Premise Edition - MDG + GRC (App ) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-mdp-cus-pr | mdpap05use2pr | 10.214.24.227 | sapmdpap05pr | 10.214.24.228 | NA | NA | NA
Apache Webserver (Non-SAP ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-mfp-cus-pr | mfpap01use2pr | 10.214.24.219 | sapmfpap01pr | 10.214.24.220 | NA | NA | NA
SAP Business Process Automation by Redwood (ASCS ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-rbp-cus-pr | rbpcs01use2pr | 10.214.24.193 | saprbpcs01pr | 10.214.24.194 | sap-ilb-rbpapp-cus-pr-01 | 10.214.24.113 | ASCS
SAP Business Process Automation by Redwood (ERS ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-rbp-cus-pr | rbpcs02use2pr | 10.214.24.203 | saprbpcs02pr | 10.214.24.204 |  | 10.214.24.112 | ERS
SAP Solution Manager 7.2 (JAVA) (ASCS+PAS ) | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-sjp-cus-pr | sjpcs01use2pr | 10.214.24.181 | sapsjpcs01pr | 10.214.24.182 | sap-ilb-sjpapp-cus-pr-01 | 10.214.24.115 | ASCS
SAP Solution Manager 7.2 (JAVA) (ERS ) | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-sjp-cus-pr | sjpcs02use2pr | 10.214.24.177 | sapsjpcs02pr | 10.214.24.178 |  | 10.214.24.114 | ERS
SAP Solution Manager 7.2 (ABAP) (ASCS+PAS ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-smp-cus-pr | smpcs01use2pr | 10.214.24.249 | sapsmpcs01pr | 10.214.24.250 | sap-ilb-smpapp-cus-pr-01 | 10.214.24.117 | ASCS
SAP Solution Manager 7.2 (ABAP) (ERS ) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-smp-cus-pr | smpcs02use2pr | 10.214.24.251 | sapsmpcs02pr | 10.214.24.252 |  | 10.214.24.116 | ERS
IaaS Basic (Vertex SIC) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-vsp-cus-pr | vspap01use2pr | 10.214.24.243 | sapvspap01pr | 10.214.24.244 | NA | NA | NA
SAP Webdispatcher (App ) | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-wpd-cus-pr | wpdap01use2pr | 10.214.24.235 | sapwd1ap01pr | 10.214.24.236 | NA | NA | NA
SAP Webdispatcher (App ) | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-wpd-cus-pr | wpdap02use2pr | 10.214.24.233 | sapwd2ap02pr | 10.214.24.234 | NA | NA | NA
Wily Introscope | SLES-SAP 12 SP4 | Suse_Linux | D4as_v4 | Central US | sap-rg-wly-cus-pr | wlyap01use2pr | 10.214.24.253 | sapwlyap01pr | 10.214.24.254 | NA | NA | NA
Unmanaged IaaS WTS service for customer (Non-SAP ) | WindowsServer | Win_2016 | D8as_v4 | Central US | sap-rg-wts-cus-pr | iaaswp1use2pr | 10.214.24.241 | sapwp1ap01pr | 10.214.24.242 | NA | NA | NA
SAP Router | SLES-SAP 12 SP4 | Suse_Linux |  | Central US |  | saproutuse2pr

## DNS Switching
Azure VM Name | Primary Region IP | During DR | Usage | SID
bdpap03use2pr | 10.213.34.9 | 10.214.24.245 | VM - Physical IP | BDP
sapbdpap03pr | 10.213.34.10 | 10.214.24.246 | Virtual IP | BDP
bdpap04use2pr | 10.213.34.11 | 10.214.24.247 | VM - Physical IP | BDP
sapbdpap04pr | 10.213.34.12 | 10.214.24.248 | Virtual IP | BDP
bdpcs01use2pr | 10.213.34.5 | 10.214.24.239 | VM - Physical IP | BDP
sapbdpcs01pr | 10.213.34.6 | 10.214.24.240 | Virtual IP | BDP
bdpap02use2pr | 10.213.34.7 | 10.214.24.237 | VM - Physical IP | BDP
sapbdpap02pr | 10.213.34.8 | 10.214.24.238 | Virtual IP | BDP
bipcs01use2pr | 10.213.34.13 | 10.214.24.173 | VM - Physical IP | BIP
sapbipcs01pr | 10.213.34.14 | 10.214.24.174 | Virtual IP | BIP
bipap02use2pr | 10.213.34.15 | 10.214.24.191 | VM - Physical IP | BIP
sapbipap02pr | 10.213.34.16 | 10.214.24.192 | Virtual IP | BIP
bipap03use2pr | 10.213.34.17 | 10.214.24.187 | VM - Physical IP | BIP
sapbipap03pr | 10.213.34.18 | 10.214.24.188 | Virtual IP | BIP
bipap04use2pr | 10.213.34.19 | 10.214.24.189 | VM - Physical IP | BIP
sapbipap04pr | 10.213.34.20 | 10.214.24.190 | Virtual IP | BIP
bipap05use2pr | 10.213.34.21 | 10.214.24.185 | VM - Physical IP | BIP
sapbipap05pr | 10.213.34.22 | 10.214.24.186 | Virtual IP | BIP
bipap06use2pr | 10.213.34.23 | 10.214.24.183 | VM - Physical IP | BIP
sapbipap06pr | 10.213.34.24 | 10.214.24.184 | Virtual IP | BIP
bipap07use2pr | 10.213.34.25 | 10.214.24.179 | VM - Physical IP | BIP
sapbipap07pr | 10.213.34.26 | 10.214.24.180 | Virtual IP | BIP
bipap08use2pr | 10.213.34.27 | 10.214.24.175 | VM - Physical IP | BIP
sapbipap08pr | 10.213.34.28 | 10.214.24.176 | Virtual IP | BIP
fipcs01use2pr | 10.213.34.31 | 10.214.24.197 | VM - Physical IP | FIP
sapfipcs01pr | 10.213.34.32 | 10.214.24.108 | Load Balancer Front End IP | FIP
sapfipap01pr | 10.213.34.90 | 10.214.24.198 | Virtual IP | FIP
fipcs02use2pr | 10.213.34.33 | 10.214.24.195 | VM - Physical IP | FIP
sapfipcs02pr | 10.213.34.34 | 10.214.24.109 | Load Balancer Front End IP | FIP
sapfipap02pr | 10.213.34.91 | 10.214.24.196 | Virtual IP | FIP
fipap03use2pr | 10.213.34.35 | 10.214.24.221 | VM - Physical IP | FIP
sapfipap03pr | 10.213.34.36 | 10.214.24.222 | Virtual IP | FIP
fipap04use2pr | 10.213.34.37 | 10.214.24.199 | VM - Physical IP | FIP
sapfipap04pr | 10.213.34.38 | 10.214.24.200 | Virtual IP | FIP
hapcs01use2pr | 10.213.34.39 | 10.214.24.201 | VM - Physical IP | HAP
saphapcs01pr | 10.213.34.40 | 10.214.24.106 | Load Balancer Front End IP | HAP
saphapap01pr | 10.213.34.88 | 10.214.24.202 | Virtual IP | HAP
hapcs02use2pr | 10.213.34.41 | 10.214.24.213 | VM - Physical IP | HAP
saphapcs02pr | 10.213.34.42 | 10.214.24.107 | Load Balancer Front End IP | HAP
saphapap02pr | 10.213.34.89 | 10.214.24.214 | Virtual IP | HAP
hapap03use2pr | 10.213.34.43 | 10.214.24.217 | VM - Physical IP | HAP
saphapap03pr | 10.213.34.44 | 10.214.24.218 | Virtual IP | HAP
hapap04use2pr | 10.213.34.45 | 10.214.24.210 | VM - Physical IP | HAP
saphapap04pr | 10.213.34.46 | 10.214.24.211 | Virtual IP | HAP
hapap05use2pr | 10.213.34.47 | 10.214.24.206 | VM - Physical IP | HAP
saphapap05pr | 10.213.34.48 | 10.214.24.207 | Virtual IP | HAP
hapap06use2pr | 10.213.34.49 | 10.214.24.205 | VM - Physical IP | HAP
saphapap06pr | 10.213.34.50 | 10.214.24.212 | Virtual IP | HAP
hapap07use2pr | 10.213.34.51 | 10.214.24.208 | VM - Physical IP | HAP
saphapap07pr | 10.213.34.52 | 10.214.24.209 | Virtual IP | HAP
hapap08use2pr | 10.213.34.53 | 10.214.24.215 | VM - Physical IP | HAP
saphapap08pr | 10.213.34.54 | 10.214.24.216 | Virtual IP | HAP
mdpcs01use2pr | 10.213.34.55 | 10.214.24.223 | VM - Physical IP | MDP
sapmdpcs01pr | 10.213.34.56 | 10.214.24.111 | Load Balancer Front End IP | MDP
sapmdpap01pr | 10.213.34.92 | 10.214.24.224 | Virtual IP | MDP
mdpcs02use2pr | 10.213.34.57 | 10.214.24.229 | VM - Physical IP | MDP
sapmdpcs02pr | 10.213.34.58 | 10.214.24.110 | Load Balancer Front End IP | MDP
sapmdpap02pr | 10.213.34.93 | 10.214.24.230 | Virtual IP | MDP
mdpap03use2pr | 10.213.34.59 | 10.214.24.225 | VM - Physical IP | MDP
sapmdpap03pr | 10.213.34.60 | 10.214.24.226 | Virtual IP | MDP
mdpap04use2pr | 10.213.34.61 | 10.214.24.231 | VM - Physical IP | MDP
sapmdpap04pr | 10.213.34.62 | 10.214.24.232 | Virtual IP | MDP
mdpap05use2pr | 10.213.34.63 | 10.214.24.227 | VM - Physical IP | MDP
sapmdpap05pr | 10.213.34.64 | 10.214.24.228 | Virtual IP | MDP
mfpap01use2pr | 10.213.33.6 | 10.214.24.219 | VM - Physical IP | MFP
sapmfpap01pr | 10.213.33.7 | 10.214.24.220 | Virtual IP | MFP
rbpcs01use2pr | 10.213.34.69 | 10.214.24.193 | VM - Physical IP | RBP
saprbpcs01pr | 10.213.34.70 | 10.214.24.113 | Load Balancer Front End IP | RBP
saprbpap01pr | 10.213.34.94 | 10.214.24.194 | Virtual IP | RBP
rbpcs02use2pr | 10.213.34.71 | 10.214.24.203 | VM - Physical IP | RBP
saprbpcs02pr | 10.213.34.72 | 10.214.24.112 | Load Balancer Front End IP | RBP
saprbpap02pr | 10.213.34.95 | 10.214.24.204 | Virtual IP | RBP
saproutuse2pr | 10.213.1.100 |  | VM - Physical IP | saprouter
sjpcs01use2pr | 10.213.34.73 | 10.214.24.181 | VM - Physical IP | SJP
sapsjpcs01pr | 10.213.34.74 | 10.214.24.115 | Load Balancer Front End IP | SJP
sapsjpap01pr | 10.213.34.96 | 10.214.24.182 | Virtual IP | SJP
sjpcs02use2pr | 10.213.34.75 | 10.214.24.177 | VM - Physical IP | SJP
sapsjpcs02pr | 10.213.34.76 | 10.214.24.114 | Load Balancer Front End IP | SJP
sapsjpap02pr | 10.213.34.97 | 10.214.24.178 | Virtual IP | SJP
smpcs01use2pr | 10.213.34.77 | 10.214.24.249 | VM - Physical IP | SMP
sapsmpcs01pr | 10.213.34.78 | 10.214.24.117 | Load Balancer Front End IP | SMP
sapsmpap01pr | 10.213.34.98 | 10.214.24.250 | Virtual IP | SMP
smpcs02use2pr | 10.213.34.79 | 10.214.24.251 | VM - Physical IP | SMP
sapsmpcs02pr | 10.213.34.80 | 10.214.24.116 | Load Balancer Front End IP | SMP
sapsmpap02pr | 10.213.34.99 | 10.214.24.252 | Virtual IP | SMP
vspap01use2pr | 10.213.33.8 | 10.214.24.243 | VM - Physical IP | VSP
sapvspap01pr | 10.213.33.9 | 10.214.24.244 | Virtual IP | VSP
wpdap01use2pr | 10.213.34.81 | 10.214.24.235 | VM - Physical IP | WD1
sapwd1ap01pr | 10.213.34.82 | 10.214.24.236 | Virtual IP | WD1
wpdap02use2pr | 10.213.34.83 | 10.214.24.233 | VM - Physical IP | WD2
sapwd2ap02pr | 10.213.34.84 | 10.214.24.234 | Virtual IP | WD2
wlyap01use2pr | 10.213.34.85 | 10.214.24.253 | VM - Physical IP | Wily
sapwlyap01pr | 10.213.34.86 | 10.214.24.254 | Virtual IP | Wily
iaaswp1use2pr | 10.213.33.12 | 10.214.24.241 | VM - Physical IP | WP1
sapwp1ap01pr | 10.213.33.13 | 10.214.24.242 | Virtual IP | WP1

## DR DB VM Details
Component | Region | Azure VM Name | VM Primary IP | Virtual Hostname1 | VM Secondary IP1 | SID | Environment Type | OS Version | OS Type | Series | ASR Region | ASR Resource Group | ASR VNET Resource Group | ASR VNET | ASR Subnet | ASR Availablity Set | ASR PPG Name | Azure VM Name | VM Primary IP | Virtual Hostname1 | VM Secondary IP1 | ASR Primary IP | ASR Secondary IP | Load Balancer Name | Load Balancer Front end IP | LB
SAP BusinessObjects Business Intelligence platform (Bobj) (ASE DB ) | Secondary Region | bipdb01cusdr | 10.214.26.64 | sapbipdb01dr | 10.214.26.65 | BIP | DR-Production(DB) | SLES-SAP 12 SP4 | Suse_Linux | D8as_v4 | Central US | sap-rg-bip-cus-dr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-db-qa | sap-avs-bipdb-cus-pr | sap-ppg-bip-cus-pr
SAP Solution Manager 7.2 (HANA DB ) | Secondary Region | smpdb01cusdr | 10.214.26.68 | sapsmpdb01dr | 10.214.26.69 | SMP/SJP | DR-Production(DB) | SLES-SAP 12 SP4 | Suse_Linux | M32ls | Central US | sap-rg-smp-cus-dr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-db-qa | sap-avs-smpdb-cus-pr | sap-ppg-smp-cus-pr
Fiori for S/4HANA On-Premise Edition (ASE DB ) | Secondary Region | fipdb01cusdr | 10.214.26.70 | sapfipdb01dr | 10.214.26.71 | FIP | DR-Production(DB) | SLES-SAP 12 SP4 | Suse_Linux | D16as_v4 | Central US | sap-rg-fip-cus-dr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-db-qa | sap-avs-fipdb-cus-pr | sap-ppg-fip-cus-pr
SAP HANA-EIM (HANA DB ) | Secondary Region | eipdb01cusdr | 10.214.26.72 | sapeipdb01dr | 10.214.26.73 | EIP | DR-Production(DB) | SLES-SAP 12 SP4 | Suse_Linux | M128S | Central US | sap-rg-eip-cus-dr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-db-qa | sap-avs-eipdb-cus-dr | sap-ppg-eip-cus-pr
SAP HANA-EIM (HANA DB ) | Secondary Region | eipdb02cusdr | 10.214.26.74 | sapeipdb02dr | 10.214.26.75 | EIP | DR-Production(DB) | SLES-SAP 12 SP4 | Suse_Linux | M128S | Central US | sap-rg-eip-cus-dr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-db-qa | sap-avs-eipdb-cus-dr | sap-ppg-eip-cus-pr
SAP HANA-EIM (HANA DB ) | Secondary Region | eipdb03cusdr | 10.214.26.76 | sapeipdb03dr | 10.214.26.77 | EIP | DR-Production(DB) | SLES-SAP 12 SP4 | Suse_Linux | M128S | Central US | sap-rg-eip-cus-dr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-db-qa | sap-avs-eipdb-cus-dr | sap-ppg-eip-cus-pr
SAP HANA-EIM (HANA DB )- StandBy | Secondary Region | eipdb04cusdr | 10.214.26.78 | sapeipdb04dr | 10.214.26.79 | EIP | DR-Production(DB) | SLES-SAP 12 SP4 | Suse_Linux | M128S | Central US | sap-rg-eip-cus-dr | sap-rg-network-cus-qa | sap-vn-cus-qa | sap-sn-db-qa | sap-avs-eipdb-cus-dr | sap-ppg-eip-cus-pr | [6 empty] | NA | NA | NA

## DR Test Steps
Planned SIDs: A1P, F3P | [6 empty] | Planned |  |  |  | Actual
Sl No. | Activity Phase | Activity Type | Activity | Org | Owner | POC | Effort (Min) | Start Date (EST) | End Date (EST) | Status | Effort (Min) | Start Date (EST) | End Date (EST) | Remarks
1 | Preparatory | Task | Pre-Checks 1- No lock on Resoure group (Primary and DR both) 2-Check and confirm core quota in Central US | Accenture | Infra |  | 15 |  |  | Complete
2 | Preparatory | Task | Check SAP Applications status from SAP GUI and Web Browsers from Production East US 2. | Basis | Basis |  | 10 |  |  | Complete
3 | Preparatory | Task | Check the SAP HANA database status from SAP HANA Studio from Production East Management Server. | Hersheys | Hersheys |  | 20 |  |  | Complete
4 |  |  | Check the FW rules at Azure Central US region ( Replicate the same rules with DR IP address ) |  |  |  | 10 |  |  | Complete |  |  |  | No changes to FW
5 | Preparatory | Task | Create DR LBs same as Primary Location with Heath probe and rules details | Accenture | Infra |  | 10
6 | Preparatory | Task | Check RPO and Replication Health of the Servers in Azure portal | Accenture | Infra |  | 15 |  |  | Complete
7 | Preparatory | Task | Application Dependancy check from Basis for ASR recovery plan | Accenture | Basis, Infra |  | 5 |  |  | Complete
8 | Preparatory | Task | Create ASR failover recovery plan and add VMs to the recovery plan as per application Dependcy check | Accenture | Infra |  | 15 |  |  | Complete |  |  |  | No dependency with any other server. ASCS, ERS and App servers.
9 | Preparatory | Task | Target IP's in DR region to be provided by IC Team to Basis to update hostfile entries | Accenture | Infra |  | 15 |  |  | Complete
10 | Preparatory | Task | Confirmation of monitoring of VM Continuous Replication in place. | Accenture | Infra |  | 10 |  |  | Complete
11 | Preparatory | Task | Validate Shut down and start up sequence of servers in ASR recovery plan | Accenture | Infra |  | 10 |  |  | Complete
12 | Preparatory | Task | Check the fstab entry in Source VMs for ANF set as 00 vaule | Accenture | Infra |  | 5 |  |  | Complete
13 | Preparatory | Task | Validating and Confirmation of RPO's of Azure VM's just before failover | Accenture | Infra |  | 20 |  |  | Complete | 13
14 | Preparatory | Task | Verify DNS changes and send mail to Hersheys Network team | Accenture | Basis, Infra |  | 5 |  |  | Complete
15 | Preparatory | Task | Check the localhost file entries and make the changes as per requirement on the Dr region | Accenture | Basis, Infra |  | 10
16 | Preparatory | Task | Check Application & Database Cluster health | Accenture | Basis |  | 30 |  |  | Complete
17 | Preparatory | Task | Check Application ASCS/ERS Primary VM host | Accenture | Basis |  | 30 |  |  | Complete
18 | Preparatory | Task | Check Application PAS and AAS status | Accenture | Basis |  | 30 |  |  | Complete |  |  |  | VMEUPLAPA1P01 -> ASCS node VMEUPLAPA1P02 -> ERS Node VMEUPLAPF3P01 -> ASCS node VMEUPLAPF3P02 -> ERS Node
19 | Preparatory | Task | Check HANA Primary DB VM | Accenture | Basis |  | 30 |  |  | Complete |  |  |  | VMEUPLDBA1P02 -> Current primary DB node VMEUPLDBA1P01 -> Current Secondary DB node VMEUPLDBF3P01 -> Current primary DB node VMEUPLDBF3P02 -> Current Secondary
20 | Preparatory | Task | Check HANA HSR status to Secondary and DR | Accenture | Basis |  | 60 |  |  | Complete
21 | Preparatory | Task | Check Sybase Primary DB VM | Accenture | Basis |  | 15 |  |  | Complete
22 | Preparatory | Task | Check Sybase replication status from Fault Manager | Accenture | Basis |  | 15 |  |  | Complete
23 | Failover | Milestone | Checkpoint |  |  |  | 45 |  |  | Complete
24 | Failover | Task | Initiate failover - Trigger ASR recovery plan as per schedule plan | Accenture | Infra |  | 45 |  |  | Complete
25 | Failover | Task | Perform manual HANA failover on DR node and start HANA DB as stand-alone database (Step 3.1.1) | Accenture | Basis
26 | Failover | Task | Login to the HANA database on DR Node SYSTEMDB with SYSTEM user and do 'Perform takeover' to start the DR as standalone DB(Step 3.1.2) |  |  |  | 15 |  |  | Complete |  | 2021-09-17 23:18 | 2021-09-17 23:56
27 | Failover | Task | Disable replication on HANA secondary DB node (Step 3.1.3) | Accenture | Basis |  | 15 |  |  |  |  | 2021-09-18 00:45
28 | Failover | Task | Stop HANA DB for ILB addition to Infrastructure team | Accenture | Basis
29 | Failover | Task | Disable replication on Sybase secondary DB node (Step 3.2) | Accenture | Basis |  | 15 |  |  |  |  | 2021-09-18 00:45
30 | Failover | Task | Perform manual Sybase failover on DR node and start Sybase DB as stand-alone (Step 3.2) | Accenture | Basis |  | 5 |  |  |  |  | 2021-09-18 00:45 | 2021-09-18 00:55
31 | Failover | Task | Stop Sybase DB for ILB addition to Infrastructure team | Accenture | Basis |  | 15
32 | Failover | Task | Create new ANF volumes for usr/sap and sapmnt for target servers at DR region and copy the data from primary region servers | Accenture | Infra |  | 15
33 | Failover | Task | Make sure targetted VMs are up & running at Primary region and same VM machines got failover to Central US region with different hostname and IP add | Accenture | Infra |  | 5
34 | Failover | Task | After failover, validate below items: a. NIC property (eg. Accelerated Networking) of the VMs at Central US region and routing table b. Validate number of NIC's on target VM's matches source c. Azure load balancer (ALB) front IP, Backend Ips, Health probes, LB rules | Accenture | Infra |  | 30 |  |  | Complete | 120 | 2021-09-17 23:56 | 2021-09-18 02:00
35 | Failover | Task | After Failover, Change the Linux Cluster Resource parameters from Primary to DR and check the cluster health | Accenture | Infra |  | 15 |  |  | Complete | 30 | 2021-09-18 02:00 | 2021-09-18 02:30
36 | Failover | Task | After Failover, Enable DR ANF mount points entry in fstab and check the trans directory | Accenture | Infra |  | 30 |  |  | Complete | 45 | 2021-09-18 02:30 | 2021-09-18 03:15
37 | Failover | Task | Change Boot Dignostics Storage account from Primary to DR | Accenture | Infra |  | 15 |  |  | Complete | 30 | 2021-09-18 03:15 | 2021-09-18 03:45
38 | Failover Validation | Task | /etc/resolv.conf entries to be disable to point to localhost entries | Accenture | Infra |  | 15 |  |  | Complete | 30 | 2021-09-18 03:45 | 2021-09-18 04:15
39 | Failover Validation | Task | Validate IP address of target NIC's matches "DR Virtual Machines" target tab sheet | Accenture | Infra |  | 20 |  |  | Complete | 20 | 2021-09-18 04:15 | 2021-09-18 04:35
40 | Failover Validation | Task | Check Time zone on VM - should be UTC | Accenture | Infra |  | 30 |  |  | Complete | 20 | 2021-09-18 04:35 | 2021-09-18 04:55
41 | Failover Validation | Task | After Failover, check the VMs at DR region are added to LB backend pool. | Accenture | Infra |  | 20 |  |  | Complete | 15 | 2021-09-18 04:55 | 2021-09-18 05:10
42 | Failover Validation | Task | After infra validation, handover VM servers to Basis team | Accenture | Infra |  | 10 |  |  | Complete | 15 | 2021-09-18 04:55 | 2021-09-18 05:10
43 | Failover Validation | Task | Perform ILB checks for Service based Applications like Web Dispatcher, WWI, SCC, SDI | Accenture | Basis |  | 15 |  |  | Complete | 15 | 2021-09-18 05:25 | 2021-09-18 05:40
44 | Failover Validation | Task | Perform Application cluster checks for ASCS/SCS/ERS on RHEL cluster with ILB | Accenture | Basis |  | 10
45 | Failover Validation | Task | Perform HANA cluster checks for SLES cluster with ILB | Accenture | Basis |  | 20
46 | Failover Validation | Task | Perform Sybase DB with ILB checks | Accenture | Basis |  | 20
47 | Failover Validation | Task | Perform R3trans DB Connectivity checks from PAS & AAS | Accenture | Basis |  | 10
48 | Failover Validation | Task | Start Primary and Additonal Application Servers | Accenture | Basis |  | 15
49 | Failover Validation | Task | Start Service based Applications and perform application sanity checks | Accenture | Basis |  | 10
50 | Failover Validation | Task | Enable cronjobs for HANA DB full backups | Accenture | Basis |  | 20
51 | Failover Validation | Task | Enable cronjobs for Sybase DB full backups, Transaction log backups and Statistics jobs | Accenture | Basis |  | 15
52 | DR Testing | Milestone | Handover to Hersheys for Application Testing |  |  |  | 5
53 | DR Testing | Milestone | Hershey's confirmation and conclusion on DR Testing |  |  |  | 10
54 | Clean-up | Milestone | Conclusion of DR Drill |  |  |  | NA
55 | Clean-up | Task | Disable cronjobs for Sybase DB full backups, Transaction log backups and Statistics jobs | Accenture | Basis |  | NA
56 | Clean-up | Task | Disable HANA DB full backups through DB13 | Accenture | Basis |  | NA
57 | Clean-up | Task | Stop Primary and Additonal Application Servers | Accenture | Basis |  | 10
58 | Clean-up | Task | Stop the ASCS/ERS service along with cluster services | Accenture | Basis |  | 5
59 | Clean-up | Task | Enable HSR on HANA DR node from Secondary Node 2 and perform sync | Accenture | Basis |  | 15
60 | Clean-up | Task | Enable SRS with manual Materialization on Sybase DR node from Primary Node 1 and perform sync | Accenture | Basis |  | 20
61 | Clean-up | Task | Cleanup DR Resources on Central US region from Azure Portal | Accenture | Infra |  | 30
62 | Transition | Milestone | Documentation | Accenture | BASIS, Infra |  | 300
63 | Transition | Milestone | Handover Documentation to Hersheys | Accenture | BASIS, Infra |  | 30
64
65

## BASIS Steps
3.1.1 | Manual failover to US West by logging as <sid>adm on US West VMs | [5 empty] | Steps for SAP HANA DR Node to be started:
| System | DB SID | DR Hostname | IP Address | Instance Number |  | 1. Login to the US West VM on DR side using <sid>adm
| SAP Fiori PLM | F3P | VMWUPLDBF3P01/sapf3pdb04 | 10.137.2.27/10.137.2.28 | 0 |  | 2. Perform “hdbnsutil -sr_takeover”
3. SAP HANA servers should start on the host and disconnect from US East Secondary Node 2.
4. Issue command ‘HDB info’ to check services are up.
5. Login to the VM on Secondary node using <sid>adm
6. Disable replication on US East Secondary Node 2 by performing “hdbnsutil –sr_unregister”
3.2 | Manual failover to US West by logging with Hershey ID and switch to syb<sid> on US West ASE VMs
| System | DB SID | Primary Node | IP Address | DR Node | IP Address
| SAP ADS | A1P | VMEUPLDBA1P01 | 10.135.2.5 | VMWUPLDBA1P01 | 10.137.2.21
|  |  | sapa1pdb02 | 10.135.2.6 | sapa1pdb04 | 10.137.2.22

## Contacts
# | Team |  | Contact Name | Primary | Secondary | Email
1 | Infra | BHF_IC@accenture.com | hitesh.jain@accenture.com |  |  | hitesh.jain@accenture.com
2 | Firewall | BHF_SI_Basis@accenture.com
3 | DNS
4 | Basis | BHF_SI_Basis@accenture.com |  |  |  | tapan.soni@accenture.com
5 | CMS Team
6 | SAP AMS Team
7 | BHF Basis Team | bhf_gl_sap_basis_team@brighthousefinancial.com |  |  |  | chad.zimmerman1@brighthousefinancial.com
| Component | SID | Type | Database | SPOC
| SAP BusinessObjects Data Services on HANA (App ) | BDP | ABAP | HANA
| SAP BusinessObjects Business Intelligence platform (Bobj) (App ) | BIP | ABAP | Sybase
| Fiori for S/4HANA On-Premise Edition (App ) | FIP | Fiori | Sybase
| S/4HANA On-Premise Edition (App ) | HAP |  | HANA
| S/4HANA On-Premise Edition - MDG + GRC (App ) | MDP |  | HANA
| Apache Webserver (Non-SAP ) | MFP |  | -
| SAP Business Process Automation by Redwood (App ) | RBP |  | HANA
| SAP Solution Manager 7.2 (JAVA) (App ) | SJP
| SAP Solution Manager 7.2 (ABAP) (App ) | SMP |  | HANA
| IaaS Basic (Vertex SIC) | VSP |  | -
| SAP Webdispatcher (App ) | WD1 |  | -
| Wily Introscope | Wily |  | -
| Unmanaged IaaS WTS service for customer (Non-SAP ) | WP1 | Terminal Server | -
| SAP Router | saprouter | saprouter | -
| SAP HANA-EIM (HANA DB ) | EIP

## Challenges - Phase1
Sl NO. | Issues | Solution | View for DR Phase II | Remarks
1 | wrong Files and directory permissions | #We have noticed this issue where we have copieed the data before failover. #We mounted the CRR ANF volumes to targets system and copy the data from the CRR ANF volume with permissions on target servers | we need to copy the data after failover completed to mitigate this issue
2 | After failover secondary NIC on one server not accessable | We had re-configured the routing table, then issue got resolved and secondary NIC started respoding | Need to follow the same solution
3 | create mount for HANA/backup | #Hana backup mount is configured with CRR volume, so it will not allow to write any data when primary region is active. #We have created the new volume\disk with 500GB volume and created a same mount as earlier #Once activity completed, we have reverted the fastab entries and deleted the newly created volume | Need to follow this solution for HANA database servers where CRR ANF volume is configured at DR region
4 | Pacemaker Cluster issue | #After restoring Pacemaker Cluster Nodes on DR Region, we have faced the Situation of Split Brain 1)Reconfiguration of Azure Fence Agent. Within CRM Configuration, Parameters like Resource Group, Host Mappings should be changed with respect to DR. 2) Reconfiguration of corosync Parameters IP Addresses to be changed in /etc/corosync/corosync.conf. If hostnames are maintained in corosysnc.conf, then populate /etc/hosts file with right IP addresses along with hostnames. | Need to follow the same solution
5 | DAA file not replicated properly on A1P app servers | # Noticed some DAA files missed in A1P application servers # copied the files from primary region servers to DR target servers manually | this is unexpected issues, it happened only on these servers, need to monitor it in phase II
6 | autofs mount issues | 1) Changing IP Address of ANF Mounts in Autofs Configuration 2) Edit the autofs.direct file /etc/autofs.direct 3) Change the IP Address so that it will align with DR region 4) Restart the Autofs Service (systemctl restart autofs.service) | Need to follow the same solution

## BASIS Learnings - Phase 1
Sl NO. | Issues | Solution | View for DR Phase II | Remarks
1 | Team had disbaled the replication and started the DR DB which leads the system replication disconnection with secondary DB. | First Basis team needs to run takeover in DR node and then they needs to disable replication from secondary node to DR site. This will help to run smoothly failover of DR and failback to Primary site.
2 | While doing failback of F3P DB Basis team identified that connectivity of DR DB to Secondary DB was failed. | Team had removed the HSR connectivity of DR node with secondary and Primary DB, reestablish the connectivity again and run full HSR which works